## Activity List
MedCare Helpdesk – Project Activity List (48 Work Packages)
WBS Code | Activity / Task Name | Task Owner | Duration (Days) | Start Date | Due Date | Predecessors
1 | PHASE 1: PROJECT MANAGEMENT | Ana-Maria-Cristina Peca (Lead) | 68 days | 19.10.2026 | 21.01.2027 | -
1.1 | Write Project Charter | Ana-Maria-Cristina Peca | 3 days | 19.10.2026 | 21.10.2026 | -
1.2 | Estimate Budget, Resources & Main Risks | Ana-Maria-Cristina Peca | 3 days | 22.10.2026 | 26.10.2026 | 1.1
1.3 | Write Project Scope Statement | Ana-Maria-Cristina Peca | 3 days | 27.10.2026 | 29.10.2026 | 1.1
1.4 | Create WBS Diagram and Activity List | Ana-Maria-Cristina Peca | 4 days | 30.10.2026 | 04.11.2026 | 1.2, 1.3
1.5 | Set Up Project Folder and Git Repository | Alexandru-Cristian-George Șerban | 2 days | 02.11.2026 | 03.11.2026 | 1.3
1.6 | Set Testing Rules and Quality Checklist | Ștefan-Andrei Necșulea | 3 days | 02.11.2026 | 04.11.2026 | 1.3
1.7 | Run Weekly Team Meetings (Meeting Minutes) | Ana-Maria-Cristina Peca | 5 days | 05.11.2026 | 15.01.2027 | 1.4
1.8 | Team Feedback Forms & Final Project Wrap-Up | Ana-Maria-Cristina Peca | 4 days | 18.01.2027 | 21.01.2027 | 6.6
2 | PHASE 2: HOSPITAL REQUIREMENTS & PLANNING | Oana-Adriana Stan (Lead) | 8 days | 02.11.2026 | 11.11.2026 | 1.3
2.1 | Analyze Hospital Needs (Equipment, Software, Staff) | Oana-Adriana Stan | 4 days | 02.11.2026 | 05.11.2026 | 1.3
2.2 | Write App Features and Requirements List | Oana-Adriana Stan | 4 days | 06.11.2026 | 11.11.2026 | 2.1
2.3 | Set Response Time Rules (SLA) by Urgency | Alexandru-Cristian-George Șerban | 3 days | 04.11.2026 | 06.11.2026 | 1.5
2.4 | Define User Roles and Access Rights (4 Roles) | David-Andrei Nică | 3 days | 05.11.2026 | 09.11.2026 | 2.1
2.5 | List Hospital Wards and Problem Categories | Darius-Adonis-Ionuț Ploae | 3 days | 05.11.2026 | 09.11.2026 | 2.1
2.6 | Plan Easy-to-Use Page Layouts for Hospital Staff | Andrei Popa-Ion | 3 days | 06.11.2026 | 10.11.2026 | 2.1
2.7 | Define Ticket Form Fields and File Upload Rules | Iulian-Marian Oprea | 3 days | 06.11.2026 | 10.11.2026 | 2.1
2.8 | Write Main Test Plan and Acceptance Checklist | Ștefan-Andrei Necșulea | 3 days | 09.11.2026 | 11.11.2026 | 1.6, 2.2
3 | PHASE 3: SYSTEM DESIGN & DIAGRAMS | Alexandru-Cristian-George Șerban (Lead) | 9 days | 09.11.2026 | 19.11.2026 | Phase 2
3.1 | Draw Use-Case and Activity Diagrams | Oana-Adriana Stan | 3 days | 12.11.2026 | 16.11.2026 | 2.2
3.2 | Design Code Structure (MVC, Repositories, Services) | Alexandru-Cristian-George Șerban | 4 days | 09.11.2026 | 12.11.2026 | 2.3
3.3 | Design Database Tables and Connections (ER Diagram) | Darius-Adonis-Ionuț Ploae | 4 days | 10.11.2026 | 13.11.2026 | 2.5
3.4 | Design Login System and Role Security | David-Andrei Nică | 3 days | 10.11.2026 | 12.11.2026 | 2.4
3.5 | Draw Page Sketches for the 4 Role Dashboards | Andrei Popa-Ion | 4 days | 11.11.2026 | 16.11.2026 | 2.6
3.6 | Draw Page Sketches for Ticket Forms & Help Guides | Iulian-Marian Oprea | 3 days | 11.11.2026 | 13.11.2026 | 2.7
3.7 | Plan Help Guides (Knowledge Base) Topics & Layout | Oana-Adriana Stan | 3 days | 17.11.2026 | 19.11.2026 | 3.1
3.8 | Write Step-by-Step Test Scenarios for Each Module | Ștefan-Andrei Necșulea | 4 days | 12.11.2026 | 17.11.2026 | 2.8
4 | PHASE 4: DATABASE & BACK-END CODING | Darius Ploae, David Nică, Alexandru Șerban | 22 days | 16.11.2026 | 15.12.2026 | Phase 3
4.1 | Code Database Models and Create SQL Tables | Darius-Adonis-Ionuț Ploae | 4 days | 16.11.2026 | 19.11.2026 | 3.3
4.2 | Code Data Saving Classes (Repositories) | Darius-Adonis-Ionuț Ploae | 4 days | 20.11.2026 | 25.11.2026 | 4.1
4.3 | Code Login, Logout and User Profile Logic | David-Andrei Nică | 4 days | 26.11.2026 | 01.12.2026 | 3.4, 4.2
4.4 | Code Staff Account Management for Admins | David-Andrei Nică | 4 days | 02.12.2026 | 07.12.2026 | 4.3
4.5 | Code Hospital Wards (Departments) Management | Darius-Adonis-Ionuț Ploae | 4 days | 26.11.2026 | 01.12.2026 | 4.2
4.6 | Code Problem Categories Management | David-Andrei Nică | 4 days | 08.12.2026 | 11.12.2026 | 4.2
4.7 | Code Main Ticket Logic and Response Timers (SLA) | Alexandru-Cristian-George Șerban | 5 days | 02.12.2026 | 08.12.2026 | 4.2, 4.5
4.8 | Code Ticket Controller, Comments and File Uploads | Alexandru-Cristian-George Șerban | 5 days | 09.12.2026 | 15.12.2026 | 4.7
5 | PHASE 5: FRONT-END PAGES & HELP GUIDES | Andrei Popa-Ion & Iulian-Marian Oprea | 27 days | 17.11.2026 | 23.12.2026 | Phase 3, 4
5.1 | Code Back-End for Help Guides (Knowledge Base) | Oana-Adriana Stan | 5 days | 10.12.2026 | 16.12.2026 | 3.7, 4.6
5.2 | Build Navigation Menus for the 4 User Roles | Andrei Popa-Ion | 4 days | 17.11.2026 | 20.11.2026 | 3.5
5.3 | Build Home Dashboards for Admin and Support Agent | Andrei Popa-Ion | 4 days | 23.11.2026 | 26.11.2026 | 5.2
5.4 | Build Home Dashboards for Medical Staff and Guest | Andrei Popa-Ion | 3 days | 27.11.2026 | 01.12.2026 | 5.2
5.5 | Build Ticket List Pages with Search and Filters | Andrei Popa-Ion | 4 days | 16.12.2026 | 21.12.2026 | 4.8, 5.3
5.6 | Build New Ticket Form, Ticket View & Photo Upload | Iulian-Marian Oprea | 5 days | 16.12.2026 | 22.12.2026 | 3.6, 4.8
5.7 | Build Admin Pages for Wards, Categories and Users | Iulian-Marian Oprea | 4 days | 14.12.2026 | 17.12.2026 | 4.4, 4.5, 4.6
5.8 | Build Help Guides Pages and Form Input Checks | Iulian-Marian Oprea | 4 days | 18.12.2026 | 23.12.2026 | 5.1, 5.6
6 | PHASE 6: TESTING, SAMPLE DATA & FINAL HANDOVER | Ștefan-Andrei Necșulea (QA Lead) | 19 days | 24.12.2026 | 19.01.2027 | Phase 4, 5
6.1 | Test Ticket Creation, Comments and SLA Timers | Ștefan-Andrei Necșulea | 4 days | 24.12.2026 | 29.12.2026 | 3.8, 5.5, 5.6
6.2 | Test Login Security and Role Restrictions | Ștefan-Andrei Necșulea | 4 days | 30.12.2026 | 05.01.2027 | 4.4, 6.1
6.3 | Add Notification Settings and Phone Number Checks | David-Andrei Nică | 4 days | 06.01.2027 | 11.01.2027 | 6.2
6.4 | Speed Up Database Queries and Fix Code Bugs | Alexandru-Cristian-George Șerban | 3 days | 06.01.2027 | 08.01.2027 | 6.1
6.5 | Fix Mobile Layout and Browser Display Issues | Iulian-Marian Oprea | 3 days | 08.01.2027 | 12.01.2027 | 5.8, 6.1
6.6 | Run Speed Tests and Write Final QA Test Report | Ștefan-Andrei Necșulea | 4 days | 11.01.2027 | 14.01.2027 | 6.2, 6.4, 6.5
6.7 | Add Sample Hospital Data Script and Prepare Release | Darius-Adonis-Ionuț Ploae | 3 days | 14.01.2027 | 18.01.2027 | 6.6
6.8 | Write User Manual and Prepare Final Presentation | Oana-Adriana Stan | 3 days | 15.01.2027 | 19.01.2027 | 6.6