## Project Charter
Project Information
Project Name | MedCare Helpdesk – Hospital Helpdesk Web Application |  | ID Number | SPM-HC-2026-01
Project Description | A web application built from scratch using ASP.NET Core MVC (C#), Entity Framework Core, Bootstrap, and jQuery. It gives hospital staff one simple place to report broken medical equipment, software errors, and everyday staff requests. It supports 4 user types (Administrator, Support Agent, Medical Staff, and Guest), tracks response deadlines (SLA), and includes a helpful guides section (Knowledge Base).
Project Sponsor | REGINA MARIA Private Healthcare Network (Represented by Dr. Claudiu Prica – Medical Director, Craiova)
Program Manager | Prof. Liliana Popa – Software Project Management Course Coordinator
Project Manager | Ana-Maria-Cristina Peca
Organization(s) | Faculty of Automation, Computers and Electronics – 4th Year Computer Engineering Project Team
Target Start Date | 19.10.2026 | Target End Date: | 22.01.2027
Business Need / Project Goal
Why this project is needed: Right now, when a medical device breaks or hospital software freezes, nurses and doctors have to call technicians on the phone or write it down on paper. Requests get lost, nobody knows who is fixing what, and urgent problems in critical wards (like ICU or Emergency) can be delayed. Project Goal: Build a simple, easy-to-use helpdesk website where hospital staff can quickly report problems, attach photos of error screens, and see when their issue will be fixed. Our goal is to cut down response times for urgent hospital issues by at least 40%.
Project Scope
In Scope |  |  | Out of Scope
• Building the web app in ASP.NET Core MVC (C#), SQL database, Bootstrap, and jQuery. • Creating, assigning, and tracking support tickets with status updates, priorities, comments, and photo uploads. • Managing hospital departments (wards) and problem categories. • Automatic deadline tracking (SLA) based on how urgent the problem is. • A "Knowledge Base" page with simple step-by-step guides for common issues. • Separate login accounts and dashboards for Admins, Support Agents, Medical Staff, and Guests. |  |  | • Separate mobile apps for iOS or Android (the website will work on phones and tablets through the browser). • Physically repairing broken medical machines. • Saving private patient medical data or diagnoses (the app is only for staff and equipment problems). • Billing, accounting, or buying spare parts from suppliers. • Connecting hardware sensors directly to old hospital machines.
Constraints | • Deadline: Must be finished by January 22, 2027 (14 semester weeks; 48 tasks / 176 working days / 1,408 hours). • Budget limit: 42,000 EUR (estimated project budget). • Code structure: Clean separation between database access, main app logic, and web pages (MVC).
Key Risks | • Risk 1: Delays when connecting the front-end web pages with the back-end code across an 8-person team. • Risk 2: Adding too many extra features during the semester and running out of time. • Risk 3: Team members being busy with other university exams and lab tests.
Assumptions | • All 8 team members have the required tools installed (Visual Studio, SQL Server, Git). • Hospital computers have local network access and a standard web browser.
Project Budget | 42,000 EUR (Estimated budget covering 1,408 hours of student development, testing, and setup)
Project Team |  | Key Project Milestones
Name | Role | # | Milestone Description & Target Date
1. Ana-Maria-Cristina Peca | Project Manager (Planning, WBS, Risk Tracking, Weekly Meetings) | 1 | M1 (04.11.2026): Project Charter, Scope Statement, WBS & Activity List finished
2. Alexandru-Cristian-George Șerban | Lead Back-End Developer (Ticket Logic, Response Timers / SLA, Git Setup) | 2 | M2 (11.11.2026): Hospital requirements, urgency rules (SLA) & Test Plan defined
3. Andrei Popa-Ion | Lead Front-End Developer (Page Layouts, 4 Dashboards, Ticket Lists) | 3 | M3 (19.11.2026): App structure, database diagram & page sketches finished
4. Darius-Adonis-Ionuț Ploae | Database Developer (Database Tables, Hospital Wards, Initial Test Data) | 4 | M4 (25.11.2026): Database tables and basic data-saving code ready
5. David-Andrei Nică | Back-End Developer (Login, User Roles, Staff Accounts, Problem Categories) | 5 | M5 (11.12.2026): User login, security roles, hospital wards & categories ready
6. Oana-Adriana Stan | Business Analyst & Back-End Dev (Requirements, Diagrams, Help Guides, Manual) | 6 | M6 (15.12.2026): Main ticket system, comments, photo uploads & timers ready
7. Iulian-Marian Oprea | Front-End Developer (Ticket Forms, Photo Uploads, Admin Pages, Form Checks) | 7 | M7 (23.12.2026): All web pages, dashboards & help guides (Knowledge Base) finished
8. Ștefan-Andrei Necșulea | QA Tester (Test Plan, Testing Features, Security Checks & Final Bug Report) | 8 | M8 (21.01.2027): Full app testing, sample hospital data loaded & final presentation